Passing the Torch Meeting

JR & JG 02/15/2010

Purpose:

The Passing of the Torch Meeting is a formal meeting to transfer all knowledge and the state of a project from Staff Liaison to the project leader.  The WSL may have been involved in project for months/years and should use this meeting to bring the PL up to speed on all aspects of the project. The meeting should also a starting point for a well planed collaborative effort between the WSL and the PL. There is no specified time before a project that the meeting should occur, but earlier is better.

Info to transfer:

- Scouting documents – And updates or changes

- Current Project Team list and leader needs

- Agency Contact info (unless WSL will be facilitating Angency relations as is the case for some projects).

- Current status of relationship with agency

- Roles grid & clarify chain of responsibility for potentially overlapping roles

- Update on status of technical design, logistical considerations, NEPA, funding issues, timeline, etc.

- Set a rough schedule for PL to implement.  Next major steps/milestones (i.e., need project planning schedule by x date).